## Sheet1
Issue key | Category | Summary | Description | Status | Assignee | Additional Assignee | Sponsor | Start Date | Due Date | Created | Updated | Last Viewed | Comments | 061119 | 06/11/19
PC-417 | Performance Management | Under â€œmanage my teamâ€ â€“ unable to view total teams goals. Can only see direct report. | Under â€œManage my Teamâ€ on the dashboardâ€“ unable to view total teams goals. Can only see direct report. | Backlog | Spencer | n/a | n/a | n/a | n/a | 43622.6056 | 43627.3639 | 43627.4424 | n/a
PC-403 | Performance Management | Performance form enhancements:â€¢ Make overall performance rating mandatory to save and submit form to the next step Test and implement | â€¢ Make overall performance rating mandatory to save and submit form to the next step Test and implement | Backlog | Daniela | n/a | n/a | n/a | n/a | 2019-06-06 14:17 | 2019-06-11 08:37 | 2019-06-11 10:37 | n/a
PC-402 | Performance Management | Performance form enhancements: â€¢ Enable self-assessment comments to be visible by the manager once submitted. | â€¢ Enable self-assessment comments to be visible by the manager once submitted. | Backlog | Daniela | n/a | n/a | n/a | n/a | 2019-06-06 14:16 | 2019-06-11 08:35 | 2019-06-11 10:37 | 11/Jun/19 8:35 AM;Spencer;Manager is able to view the associate's self assessment comments (on the right side of the screen) in the Manager's Assessments stage. Assign to Comp team for testing.
PC-401 | Performance Management | Performance form enhancements: â€¢ Turn on overall rating in self assessment forms. | â€¢ Turn on overall rating in self assessment forms. | Backlog | Daniela | n/a | n/a | n/a | n/a | 2019-06-06 14:15 | 2019-06-11 08:23 | 2019-06-11 10:37 | n/a
PC-400 | Performance Management | Performance form enhancements: â€¢ Enable self-assessment forms to be accessible by the employee throughout the performance process | â€¢ Enable self-assessment forms to be accessible by the employee throughout the performance process | Backlog | Daniela | n/a | n/a | n/a | n/a | 43622.5931 | 43627.3486 | 43627.4424 | 11/Jun/19 8:21 AM;Spencer;Associate has ability to view own self-evaluation rating through the "All Forms" and "En Route" pages. Reassigning to Comp team for testing.
PC-416 | n/a | The Overall Rating for associates should populate automatically | It was great being able to have rating overrides, however having 2 spaces to enter an overall rating almost gave managers incentive and easy way to override | Backlog | Spencer | n/a | n/a | n/a | n/a | 2019-06-06 14:32 | 2019-06-11 08:20 | 2019-06-11 10:37 | 11/Jun/19 8:20 AM;Spencer;As per the consultant, The Overall Rating for associates should could not populate automatically. We will ask for additional details on 6/12
PC-418 | n/a | Several issues with no final ratings entered | Several issues with no final ratings entered. Can we make it that the review cannot be saved if a final rating is not entered? We confirmed in Test that the review could not be saved but we are not sure if the code (behavior) is the same in production. | Backlog | Daniela | n/a | n/a | n/a | n/a | 2019-06-06 14:33 | 2019-06-11 07:40 | 2019-06-11 10:37 | 11/Jun/19 7:40 AM;Spencer;â€¢ HRMS: Confirm that Overall Rating is required in Calibration Step. â€¢ Assigning to Comp team for testing.
PC-420 | n/a | Forms for Terminated Employees | Is there a way to inactive an employee's form when they are terminated so the form is no longer visible in a manager's list? | Backlog | Spencer | n/a | n/a | n/a | n/a | 43622.609 | 43622.609 | 43627.4424 | n/a
PC-415 | n/a | Confirm Comp Calc rules: | Confirm Comp Calc rules: â€¢ Confirm application of bonus calculation rules for overrides for 2019 â€¢ Merit budget reco | Backlog | Daniela | n/a | n/a | n/a | n/a | 2019-06-06 14:29 | 2019-06-06 14:29 | 2019-06-11 10:37 | n/a
PC-414 | n/a | TBD (Daniela follows up with Carrie) | TBD (Daniela follows up with Carrie) | Backlog | Daniela | n/a | n/a | n/a | n/a | 2019-06-06 14:28 | 2019-06-06 14:28 | 2019-06-11 10:37 | n/a
PC-413 | n/a | Employee & manager communication | Employee & manager communication: â€¢ enhanced employee messaging â€¢ communications throughout the year (performance and comp, separate from eachother) â€¢ research email notifications | Backlog | Daniela | n/a | n/a | n/a | n/a | 2019-06-06 14:28 | 2019-06-06 14:28 | 2019-06-11 10:37 | n/a
PC-412 | n/a | Review issue management workflow and assignment (FL SuccessFactors, HR Services Center, HRBPs, online Q&A, etc.) | Review issue management workflow and assignment (FL SuccessFactors, HR Services Center, HRBPs, online Q&A, etc.) | Backlog | Daniela | n/a | n/a | n/a | n/a | 43622.6021 | 43622.6021 | 43627.4424 | n/a
PC-411 | Performance Management | Design and implement reporting capabilities for all modules in SuccessFactors (HRBP/Manager/Comp) | Design and implement reporting capabilities for all modules in SuccessFactors (HRBP/Manager/Comp) â€¢ define business requirements for all modules for each population â€¢ test and implement solution for full process â€¢ Give visibility to leaders and HR to the performance distribution guidelines into SuccessFactors (research SF-delievered, align, develop, test and implement) | Backlog | Spencer | n/a | n/a | n/a | n/a | 2019-06-06 14:26 | 2019-06-06 14:26 | 2019-06-11 10:37 | n/a
PC-409 | n/a | Enhanced HR access throughout the process. | Enhanced HR access throughout the process. â€¢ collect and document business requirements â€¢ research SF-delivered options and best practices â€¢ align with HRLT â€¢ develop, test and implement solution for full process | Backlog | Daniela | n/a | n/a | n/a | n/a | 2019-06-06 14:25 | 2019-06-06 14:25 | 2019-06-11 10:37 | n/a
PC-408 | n/a | Enhanced direct manager and leader access throughout the process. | Enhanced direct manager and leader access throughout the process. â€¢ collect and document business requirements â€¢ research SF-delivered options and best practices â€¢ align with HRLT â€¢ develop, test and implement solution for full process | Backlog | Daniela | n/a | n/a | n/a | n/a | 2019-06-06 14:24 | 2019-06-06 14:24 | 2019-06-11 10:37 | n/a
PC-407 | Year-End Deliverables | Enhanced associate experience throughout the process | Enhanced associate experience throughout the process â€¢ collect and document business requirements â€¢ align with HRLT â€¢ develop, test and implement solution for full process | Backlog | Daniela | n/a | n/a | n/a | n/a | 43622.5993 | 43622.5993 | 43627.4424 | n/a
PC-406 | n/a | 2020 review of Goal Library | 2020 review of Goal Library: â€¢ Define ownership and timeline for approval and align with HR â€¢ Implement and test changes before 2020 launch | Backlog | Spencer | n/a | n/a | n/a | n/a | 43622.5986 | 43622.5986 | 43627.4424 | n/a
PC-405 | Comp Planning | Comp template enhancements: â€¢ Add career level to compensation template | Comp template enhancements: â€¢ Add career level to compensation template | Backlog | Spencer | n/a | n/a | n/a | n/a | 2019-06-06 14:21 | 2019-06-06 14:21 | 2019-06-11 10:37 | n/a
PC-404 | Performance Management | Design and implement solution for delegating manager powers when manager is on leave for performance process. | Design and implement solution for delegating manager powers when manager is on leave for performance process. â€¢ research SF-delivered options and best practices â€¢ confirm and document what the role will be able to read/write at each step of the way â€¢ align with business owner (comp) â€¢ test and implement solution for full process | Backlog | Spencer | n/a | n/a | n/a | n/a | 43622.5972 | 43622.5972 | 43627.4424 | n/a
PC-399 | Year-End Deliverables | Define tools & processes to engage HR Community into the process, maintain in central location with appropriate access, leveraging Office 360 tools | â€¢ Create a HRBP facing calendar and appropriate calendar â€¢ Document library â€¢ Teams Group Management | Backlog | Daniela | Michael | n/a | n/a | n/a | 2019-06-06 13:09 | 2019-06-06 13:09 | 2019-06-11 10:37 | n/a